## Project schedule
Mobile 2000 — Project Schedule (Gantt Chart)
TASK | Day | PROGRESS | START | END | Jan 2026 |  |  |  | Feb 2026 |  |  |  | Mar 2026 |  |  |  |  | Apr 2026 |  |  |  | May 2026 |  |  |  | Jun 2026
[5 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15
Project Initiation & Planning (Gap analysis) | bar: Jan 2026 5
Project scope & objectives | 7 | 100% | 2026-01-05 | 2026-01-11 | bar: Jan 2026 5
Requirements gathering | 7 | 100% | 2026-01-12 | 2026-01-18 | bar: Jan 2026 12
Define system modules (Catalog, Cart, Finder) | 7 | 100% | 2026-01-12 | 2026-01-18 | bar: Jan 2026 12
Choose tech stack (HTML / CSS / JS) | 7 | 100% | 2026-01-19 | 2026-01-25 | bar: Jan 2026 19
Work breakdown & folder structure | 7 | 100% | 2026-01-19 | 2026-01-25 | bar: Jan 2026 19
System Design | bar: Jan 2026 5
Design system & UI style (colors / typography) | 14 | 100% | 2026-01-26 | 2026-02-08 | bar: Jan 2026 26 to Feb 2026 2
Wireframes & page layouts | 7 | 100% | 2026-02-02 | 2026-02-08 | bar: Feb 2026 2
Data model & seed data (35 products) | 7 | 100% | 2026-02-09 | 2026-02-15 | bar: Feb 2026 9
Arabic / English (RTL / LTR) plan | 7 | 100% | 2026-02-09 | 2026-02-15 | bar: Feb 2026 9
Recommendation algorithm design | 7 | 100% | 2026-02-16 | 2026-02-22 | bar: Feb 2026 16
Business process flowchart | 7 | 100% | 2026-02-16 | 2026-02-22 | bar: Feb 2026 16
Frontend Development (Coding) | bar: Jan 2026 5
Homepage, hero & widgets | 14 | 100% | 2026-02-23 | 2026-03-08 | bar: Feb 2026 23 to Mar 2026 2
Products listing + filters / sort | 7 | 100% | 2026-03-09 | 2026-03-15 | bar: Mar 2026 9
Product details page | 7 | 100% | 2026-03-16 | 2026-03-22 | bar: Mar 2026 16
Shopping cart & checkout | 7 | 100% | 2026-03-23 | 2026-03-29 | bar: Mar 2026 23
Wishlist & phone comparison (radar) | 7 | 100% | 2026-03-30 | 2026-04-05 | bar: Mar 2026 30
Smart Phone Finder wizard | 7 | 100% | 2026-04-06 | 2026-04-12 | bar: Apr 2026 6
AI assistant chatbot | 7 | 100% | 2026-04-13 | 2026-04-19 | bar: Apr 2026 13
Auth & account dashboard | 7 | 100% | 2026-04-13 | 2026-04-19 | bar: Apr 2026 13
Device-art SVG & realistic images | 7 | 100% | 2026-04-20 | 2026-04-26 | bar: Apr 2026 20
Premium v2.0 redesign | 7 | 100% | 2026-04-27 | 2026-05-03 | bar: Apr 2026 27
Integration & Testing | bar: Jan 2026 5
Integrate modules & state store | 7 | 100% | 2026-05-04 | 2026-05-10 | bar: May 2026 4
Functional & UI testing | 7 | 100% | 2026-05-11 | 2026-05-17 | bar: May 2026 11
Form validation & cart testing | 7 | 100% | 2026-05-11 | 2026-05-17 | bar: May 2026 11
Recommendation system testing | 7 | 100% | 2026-05-18 | 2026-05-24 | bar: May 2026 18
Bug fixing & refinements | 14 | 90% | 2026-05-18 | 2026-05-31 | bar: May 2026 18 to May 2026 25
Deployment & Documentation | bar: Jan 2026 5
Documentation (README, test plan, report) | 14 | 100% | 2026-06-01 | 2026-06-14 | bar: Jun 2026 1 to Jun 2026 8
Deploy to Netlify / Vercel | 7 | 30% | 2026-06-15 | 2026-06-21 | bar: Jun 2026 15
Final review & submission | 7 | 20% | 2026-06-15 | 2026-06-21 | bar: Jun 2026 15
Legend: |  | Project Initiation & Planning |  |  | Jan 2026 5: System Design; Jan 2026 26: Frontend Development; Feb 2026 16: Integration & Testing; Mar 2026 9: Deployment & Documentation